Gambia-Senegal Sustainable Fisheries Project

Year 5, Fiscal Year 2014, Quarter 2 Report

January 1 – March 31, 2014

(LWA Associate Award No. 624-A-00-09-00033-00)

THE GAMBIA

A partnership of:

United States Agency for International Development / West Africa

Coastal Resources Center, University of Rhode Island

World Wide Fund for Nature, West Africa Marine Program Office

Department of Fisheries, The Gambia

Ministry of Fisheries and Water Resources, The Gambia

# Contact Information

Dr. Bamba Banja

Project Coordinator

Gambia-Senegal Sustainable Fisheries Program (USAID/BaNafaa)

Tel: 220-779-68-11

Email: bamba.banja@yahoo.co.uk

Brian Crawford

Director, International Programs

Coastal Resources Center

University of Rhode Island

Tel: 1-401-874-6225

Fax: 1-401-874-6920

Email: brian@crc.uri.edu

Karen Kent

Project Leader

Coastal Resources Center

University of Rhode Island

Tel: 1-401-874-6630

Fax: 1-401-874-6920

Email:  karen@crc.uri.edu

Kim Kaine

Global Program Coordinator

Coastal Resources Center

University of Rhode Island

Tel: 401-874-6823

Fax: 401-874-6920

Email: kkaine@crc.uri.edu

Georgette Yarboi-Quayson

Administrative Office Technical Representative

U.S. Agency for International Development / West Africa

Tel: 233-244-532913

Email: gyarboi-quayson@usaid.gov

# Table of Contents

Page

1.	Introduction	1

1.1 Background	1

1.2 Program Goal and Intermediate Results	3

2.	Year Five, Quarter 2 Accomplishments	4

2.1 Intermediate Result 1:	4

2.1.1	Effective Sole/Multispecies Catfish Fishery Co-Management Plan	6

2.1.2	Effective Oyster and Cockle Co-Management Plan	8

2.1.3      Water, Sanitation and Hygiene (WASH)	16

2.2 Intermediate Result 2:	21

2.2.1	End of Project Stakeholder Review and Closeout Workshop.	22

2.3  Intermediate Results 3 and 4:	25

3.	Project Management	26

3.1 International Travel Schedule	26

3.2 Environmental Monitoring and Compliance	26

3.3 Branding	27

3.4 TraiNet Data on Trainings Conducted during the Reporting Period	28

3.5 Estimated Financial Status	31

Appendix A. Results Framework & Life-of-Project (LOP) Targets	47

Appendix B. USAID ROECCR Results Framework	40

Appendix C. Activity Implementation Status	40

# 1.	Introduction

The USAID/ BaNafaa project is a five-year regional initiative supported by the American people though the U.S. Agency for International Development (USAID)/West Africa Regional Mission. It is implemented through the University of Rhode Island (URI)-USAID cooperative agreement on Sustainable Coastal Communities and Ecosystems (SUCCESS). The World Wide Fund for Nature West Africa Marine Program Office (WWF-WAMPO) is a regional implementing partner.  Local partners include TRY Oyster Women’s Association (TRY), the National Sole Co-Management Committee (NASCOM), and the Water Resources Laboratory.  At the end of Year 2, Water, Sanitation and Hygiene (WASH) and Climate Change funding was added to the award in addition to previous fisheries activities under the biodiversity earmark.  URI works with local partners the Trust Agency for Rural Development (TARUD) and The Gambian Agency for Public Works (GAMWORKS) to implement WASH activities and a bilateral Climate Change Vulnerability Assessment was conducted by WWF in Year 3.  All project activities are carried out in partnership with the Department of Fisheries (DoFish) and stakeholders in the fisheries sector in The Gambia and Senegal. The focus is on sustainable fisheries management including the shared marine and coastal resources between The Gambia and Senegal. However, most field activities are in The Gambia.  The Gambia - Senegal Sustainable Fisheries Project contributes directly to the achievement of the USAID West Africa Regional Office of Environment & Climate Change Resilience (ROECCR) Results Framework through contributions to multiple Intermediate Results.

Year 5 (FY14) is the final 7 months of the project through April 30, 2014.  This report briefly describes Year 5, second quarter accomplishments (January 1, 2014 – March 31, 2013).  As of December 31, 2013, WWF sub-award activities were completed.  WASH activities, shellfish sanitation planning, and TRY and NASCOM seed grant activities leading up to but not including the final month of April are covered in this report.  A comprehensive USAID/BaNafaa Final Report will follow this report after Project completion.

## 1.1 Background

In West Africa, an estimated 1.5 million tons of fish are harvested annually from the region’s waters, with a gross retail value of US$1.5 billion.  In The Gambia and Senegal artisanal fisheries make up a majority of the fisheries landings and contribute significantly to income generation and local food security for coastal communities and for many communities inland where fish are traded. Some 200,000 people in the Gambia and 600,000 in Senegal are directly or indirectly employed in the fishing sector. Seafood products are a leading export of the region and generate as much as 20% of the gross value of exports. While the majority of seafood exports are destined for European Union (EU) markets, a growing volume of trade goes to the U.S. and other countries in the region.

Fish provides the main source of animal protein for the average rural family in the sub-region, where annual fish consumption can be as much as 25kg per capita. In many rural areas, fishing serves as a “social safety net” when farming turns unproductive due to depleted soil, drought, disease, or other factors.

In addition to direct socioeconomic benefits derived from fishing, a well-managed sector can benefit other aspects of the region’s economy and quality-of-life. This includes a growing tourism sector and a number of globally and regionally significant natural heritage areas. With annual tourist arrivals surpassing 120,000 in The Gambia and 400,000 in Senegal, a growing number of tourists are taking advantage of the countries’ ecologically significant reserves, parks, and protected areas—most of which have direct links to the fate of well-managed fisheries. These include but are not limited to the Sine-Saloum Delta Biosphere Reserve in Senegal and in The Gambia the Niumi National Park, the Baobolon Wetland Reserve, and the Tanbi Wetland Complex—all are designated Ramsar sites and contain globally significant wetlands.

The Gambia’s fisheries sector operates under the authority and responsibility of the Minister of Fisheries and Water Resources, through the Department of Fisheries (DoFish). The policy, legal and management framework for fisheries in The Gambia is provided by the 2007 Fisheries Act and the 2008 Fisheries Regulations. A draft Fisheries Management Plan for shrimp, sardinella and sole fish was prepared in 2009. The Fisheries Act mandates a Fishery Advisory Committee and Community Fisheries Centers as the institutional structure for inclusive oversight of the sector and also allows for decentralized fisheries co-management. The policy objectives of the fisheries sector as articulated in policy documents include:

•	Rational and long-term utilization of the marine and inland fisheries resources

•	Improving nutritional standards of the population

•	Increasing employment opportunities in the sector

•	Increasing foreign exchange earnings

•	Increasing and expanding the participation of Gambians in the fisheries sector

•	Improving the institutional capacity and legal framework for the management of the fisheries sector

The policy objectives of the fisheries sector are linked to key national development objectives that include: increased food self-sufficiency and security; a healthy population and enhanced employment opportunities for nationals; increased revenue generation and foreign exchange earnings; and the attainment of national social and economic development. They are designed to support key national development objectives as outlined in the Poverty Reduction Strategy Paper and The Gambia Incorporated Vision 2020, which are blueprints for national development and eradication of poverty.

## 1.2 Program Goal and Intermediate Results

The goal of the USAID/BaNafaa Project is to support the Government of The Gambia in achieving its fisheries development objectives by contributing to the following vision:

Artisanal fisheries and coastal ecosystems in The Gambia and selected stocks shared with Senegal are being managed more sustainably, incorporating significant participation of fisherfolk in decision-making, and attaining improved economic benefits for both men and women involved in the market value chain.

USAID/BaNafaa builds on the on-going efforts of the Department of Fisheries in The Gambia, working with several community fisheries centers and their management committees to improve fisherfolk involvement in the management of fisheries resources. More specifically, to further the development and implementation of the draft fisheries management plan for sole and other selected species. Sole is an important export commodity so this involves partnerships with export processing businesses as well. This is also a shared stock with Senegal.  As gender equity is another important aspect of the project, USAID/BaNafaa is benefiting both men and women in the fisheries sector by also working with oyster harvesters—a women-dominated fishery whose importance is often under-recognized.

Intermediate Results for the USAID/BaNafaa Project:

Project Strategies

- A participatory co-management approach that engages fisherfolk in decision-making.

- An ecosystem-based approach that looks not only at the fish, but protection of critical habitats and reduction of fishery impacts on threatened marine species

- Mainstreaming gender dimensions that provide opportunities for both men and women to benefit economically and participate in decision-making.

- A threats-based approach to coastal and marine biodiversity conservation.

- IR 1: Strategies to increase social and economic benefits to artisanal fishing communities, and otherwise create incentives for a sustainable fisheries agenda in the WAMER identified, tested and applied

- IR 2: Institutional capacity strengthened at all levels of governance to implement an ecosystem-based, co-management approach to sustainable fisheries, and to prevent overfishing

- IR 3: Nursery areas and spawning areas for critical life stages of commercially important species and for associated marine turtles and mammals are protected

- IR 4: Change unsustainable and destructive marine resource use practices that threaten improved biodiversity conservation in the West Africa Marine Ecoregion

Geographic Scope. The Project concentrates its activities on the marine and coastal resources and fisheries stocks shared among the Casamance, the Gambia River and Saloum Delta region—an area of regional biodiversity significance (see Figure 1). The majority of on-the-ground activities occur in The Gambia, where USAID/BaNafaa focuses on the artisanal nearshore fisheries along the Atlantic coastline as well as the estuarine- and mangrove-dominated portions of The Gambia River (see Figure 1). A sister project in Senegal, called the Wula Nafaa project, worked on fisheries management in the Saloum Delta and Casamance River. Together, these two USAID-supported initiatives are expected to have a significant impact on improved management of this biodiversity-rich area.

Gambia River estuary

Atlantic

Ocean

SENEGAL

THE GAMBIA

SENEGAL

Banjul

Figure 1. Areas of Biodiversity Significance in the WAMER and The Gambia River Estuary and Atlantic Coast

# 2.	Year Five, Quarter 2 Accomplishments

USAID/BaNafaa’s approach for Year 5 is to focus on consolidating achievements made and ensuring that measures, systems and procedures already developed are functioning and can be sustained when project assistance ends.  Institutionalizing the adaptive management process around which the two approved co-management plans were designed is a key priority as the project wraps up.  Continuing to reinforce the capacity of the government and civil society co-management institutions responsible for implementation of the two plans is also central to all Year 5 activities.

See Appendix A for The Results Framework, Indicator Results Tables, Results to Date and Life of Project Targets and Appendix C for Activity Implementation Status.

## 2.1 Intermediate Result 1:

Strategies to increase social and economic benefits to artisanal fishing communities, and otherwise create incentives for a sustainable fisheries agenda in the WAMER identified, tested and applied.

Year 5, Quarter 2 Highlights

- The Fishery Co-Management Plan for The Gambia Sole Complex approved in January 2012 was gazetted in December 2013, finalizing the process of making it a legal, enforceable plan.

- Following amendment to the Sole Co-Management Plan in December 2013 to include marine catfish, NASCOM began a catfish research activity added to its seed grant last quarter.  The study  looks at the effect of hook size on the size of catfish caught and will inform management decision-making on minimum hook size requirements.

- In response to its Letter of Inquiry submitted to the Sustainable Fisheries Fund to finance another pre-assessment of the Gambian sole fishery, URI was asked to submit a full proposal.  The assessment will enable stakeholders in The Gambia sole fishery to more concretely identify remaining gaps before a higher stakes full assessment.

- The Cockle and Oyster Fishery Co-Management Plan for the Tanbi Wetlands National Park approved in 2012 was gazetted in December 2013, finalizing the process of making it a legal, enforceable plan.

- TRY Association hosted the second annual Oyster and Cockle Co-Management Plan review meeting in January 2014.

- Shellfish water quality zones were identified, classified and mapped based on 3 years of bi-monthly water quality testing at more than 15 harvesting sites and bi-annual shoreline sanitation surveys.  This classification and mapping is the basis for a Gambian National Shellfish Sanitation Plan that is under development.  South Africa is the only other Sub-Saharan African country to have such a plan.

- TRY Association conducted a General Assembly and elections (held every 2 years) to replace its officers.

- TRY Association conducted an outreach visit to five oyster harvesting communities in Southern Senegal in the Allahein River estuary shared with The Gambia.  A joint meeting in January reaffirmed the commitment of Gambian and Senegalese communities to jointly manage shellfish resources in the transboundary estuary and identified next steps.

- 11,663 people have improved access to water and sanitation as WASH Management Plans were signed and toilets and water points handed over to communities at an additional fish landing and oyster harvesting site - Kartong.  WASH plans identify WASH Management Committees, ban open defecation and specify user fees for sustainable management of the facilities.

### 2.1.1	Effective Sole/Multispecies Catfish Fishery Co-Management Plan

The potential both for advancing the sustainable fisheries management agenda and for social and economic benefits for artisanal fishing communities in the sole fishery in The Gambia is significant as stakeholders in The Gambia continue to engage in participatory ecosystem based co-management of the artisanal Sole fishery under the approved co-management plan.  The USAID/BaNafaa project has been the most significant partner of The Gambian Government and fisheries stakeholders in this effort.  Year 5, Quarter 2 achievements described below focus on the sustainability of the co-management process as project assistance ends.

- The Sole Fishery Co-Management Plan Gazetted.

The Plan was officially gazetted on December 19, 2014, almost 3 years after approval. Gazetting finalizes the process of making it a legal, enforceable plan.  It is significant that The Gambia has accomplished this step as it is often not achieved even when fisheries management plans are approved.

Figure 2.  The Gazetted Sole and Oyster and Cockle Fishery Co-Management Plans

- Catfish Longline Research Initiated

In December 2013, an amendment to the Sole Co-Management Plan expanded its scope to a multi-species plan, including marine catfish.  Research findings show that the principal gear used to catch catfish appears to be shifting in recent years from bottom set gillnets to longlines with hooks.  As a result, stakeholders realized that the current management measures covering gillnet mesh size may not be sufficient to reduce the catch of juvenile catfish.  Stakeholders, thus, recommended a longline hook study to inform fishery management decision-making on hook size restrictions.  USAID/BaNafaa worked with NASCOM in Quarter 1 to design and budget for the study.  An amendment to NASCOM’s seed grant added this activity.  In Quarter 2, DoFish staff seconded to WWF for the USAID/BaNafaa project, who are now back at DoFish, and a Peace Corps volunteer assisted NASCOM and master fishermen to begin data collection.  The field work for the study will be completed in early April 2014 due to delays caused by bad weather.

Figure 3.  Women at Bakau landing site preparing the day’s catfish catch for sale and processing.

- Readiness for Marine Stewardship Council (MSC) provisional/conditional certification.

In Quarter 1, a report was finalized and shared with MSC that reviews progress made on the areas identified for improvement as a result of the 2008 MSC pre-assessment of the Gambian sole fishery.  Very significant progress has been made, most notably the Sole Fishery Co-Management Plan with its biological, ecological, economic and social management objectives, management measures identified to achieve these objectives, and an adaptive management approach institutionalizing continued research and application of findings for updated decision-making. The creation and granting of exclusive use rights to a representative governance body (NASCOM) is also a significant development.  Improvements are still needed in data collection for regular stock assessment and in better understanding and addressing the transboundary nature of the sole stock, its harvesting and its marketing (See bi-lateral Senegal-Gambia activities under IR 2 below).  Stakeholders have decided to pursue another MSC pre-assessment rather than risk the high stakes (in cost and reputation) of a full assessment.  Given the amount of time that has passed and the changes that have occurred in The Gambia and in MSC’s process, another pre-assessment will provide a concrete picture of where to best focus future efforts.

In December, CRC submitted a proposal to the Sustainable Fisheries Fund (SFF) to seek funding for the pre-assessment.  In Quarter 2 (March) SFF invited URI to submit a full proposal for up to $30,000 to engage an accredited firm to conduct the pre-assessment.  NASCOM has funds donated by Kaufland Seafood Company held in escrow for the eventual full assessment required for certification.

MSC continues to share the Gambia experience broadly as an example of a developing country fishery pursuing certification.  Most recently the Chief Executive of MSC wrote a Huffington Post blog article entitled, “Fish for Good in the Developing World,” citing The Gambia case and acknowledging USAID.

### 2.1.2	Effective Oyster and Cockle Co-Management Plan

Strategies to increase social and economic benefits for artisanal fishing communities and increase incentives for advancing a sustainable fisheries management agenda are strongly demonstrated in the process that led to approval of the Oyster and Cockle Co-Management Plan for the Tanbi Wetlands National Park.  Implementation of the plan and realization of the benefits are on-going.  Demand from additional shellfish harvesting communities for expansion of the process upstream in The Gambia River Estuary and in the transboundary Allahein River Estuary is a strong indicator of its impact.   Year 5, Quarter 2 achievements described below focus on the sustainability of the co-management process as project assistance ends.

- The Oyster and Cockle Fishery Co-Management Plan for the Tanbi Gazetted.

The Plan was officially gazetted in a single publication along with the Sole Plan on December 19, 2013.

- Second Annual Review Meeting for the Oyster and Cockle Co-Management Plan held.

TRY organized and hosted the review meeting on January 16, 2014.  It was officially opened by the Hon. Minister of Fisheries and Water Resources and was attended by all stakeholder institutions, members of the legislature, municipalities, local authorities, representatives of the shellfishery communities in the Tanbi Wetland National Park (TWNP) and other communities in the West Coast Region (WCR). Also, in attendance were the women shellfish harvesters and processors of the Allahein Kafoo from Casamance, Southern Senegal. Namely: Katak, Kabajo, Abene, Mamuoda, Niafrang, Donbondir and Boudouk.  Dr. Michael Rice of URI was also present.

Figure 4: From right Mrs. Fatou Janha Mboob, TRY Coordinator; Mr. Nfamara Dampha, Director of Fisheries; Hon. Minister of Fisheries and Water Resources, Mr. Mass Axi Gye; Dr. Bamba Banja, USAID/BaNafaa WASH Coordinator and Dr. Michael Rice of the University of Rhode Island.

An important outcome of this meeting was to reaffirm the commitment of stakeholder institutions to the sustainability of the Oyster and Cockle Co-Management Plan, especially as the USAID/BaNafaa Project is ending.

The Director of Fisheries expressed support to TRY and pledged the Fisheries Department’s collaboration in the implementation of the Oyster and Cockle Co-Management Plan. The Minister of Fisheries and Water Resources and the Director of Fisheries announced and handed over at the meeting a 15 horse power outboard engine bought by the EU/UNDP project for TRY Association. Other forms of support given by the Department of Fisheries presented at the meeting include the following:

- Attachment of two personnel of DoFish to the USAID/BaNafaa project under WWF to render support through skills transfer in aquaculture.

- A Fisheries Department staff sits at the board level participating the planning and management of TRY.

- Support for mangrove regeneration.

- Support for strategy development.

- Program development and implementation.

- Participation in research on the culturing of oysters.

- Participation in research on cockle ranching.

Mr. Hatab Camara of the Department of Forestry summarized the role of his Department in the implementation of the Plan as follows:

•	Conducting periodic research

•	Awareness creation

•	Promoting the participatory approach

•	Mangrove planting

•	Law enforcement

•	Programs and Projects to support mangrove management

The role of the National Environment Agency (NEA) in the implementation of the Plan was presented by Mr. Nfamara Drammeh, NEA Program Officer.  These fall under four main categories as follows:

1.	Monitoring essential habitat quality and status of the mangrove ecosystem

2.	Conducting research and vulnerability assessment on impacts of climate change

3.	Coordinating the activities of stakeholders within the coastal zone through the Coastal and Marine Working Group (CMWG) and

4.	Support to TRY Oyster Women’s Association

The NEA has in collaboration with other stakeholder institutions participated in the sanitary shoreline surveys within the TWNP and other oyster harvesting communities in the West Coast Region to determine pollution sources. Also, the NEA conducts monitoring of dumping sites and joint clean-up exercises of TWNP with WWF. Other activities include the production of Land Use/Land Cover maps of the TWNP.  Going forward, the NEA will be storing GIS data and mapping the water quality classification zones of shellfish harvesting areas. Furthermore, the Agency serves as the platform for conflict resolution among stakeholders within the coastal zone in accordance with the National Environment Management Act 1994. Finally, two coastal projects of US$ 8.9M and US$ 5.3M are starting up in January 2014 and TRY is a potential beneficiary subject to the submission of project proposals.

The role of the Department of Parks and Wildlife Management (DPWM) was presented by Mr. Nuha Jammeh as follows:

- Ensuring that the TWNP is strictly managed to prevent unlawful exploitation of resources

- Ensuring that bio-rights are adequately utilized by the people of the communities’ peripheral to the TWNP and in accordance with the National Biodiversity Act.

- Routine patrol and surveillance in the TWNP to prevent illegal activities and over exploitation

- Information sharing with oyster women in the field

- Collaboration with TRY Association in oyster culture at the various sites

- Participant of the oyster and cockle committees

To the surprise of TRY and other stakeholders, the DPWM representative expressed that the DPWM did not feel it had been adequately involved in the preparation of the Co-Management Plan.  Taking this comment very seriously, TRY and the other stakeholders organized a follow-up meeting on January 23, 2014 to more thoroughly address this feedback.  At the meeting, the process of development of the plan since 2009 was reviewed and the concerns of the current DPWM representative were satisfied regarding the authorities of each agency and TRY.  DPWM is now satisfied that TRY’s activities along with the support and authority granted to it by the Department of Fisheries under the Fisheries Act of 2007 will make a significant contribution and will pose no risk to the objectives and the authority of DPWM in the TWNP.  The capacity of TRY and stakeholder agencies to successfully address concerns such as this when they arise attests to the strength of the partnerships forged and the common vision established in the co-management planning process.

- Development of a Gambia National Shellfish Sanitation Plan.

USAID/BaNafaa support for water quality testing for 3 consecutive years at 15 oyster harvesting sites within Tanbi Wetlands and Western Region, and at 4 additional harvesting sites deep inside the Tanbi starting in January 2013, ended in December 2013.  Results are shown in Figures 5 and 6 below.  The data shows encouraging results as detailed in previous progress reports.  The results from inside the Tanbi are among the lowest counts in tropical oyster growing grounds.  The results suggest that a shellfish sanitation program could allow for the safe harvest of live oysters for a raw oyster market to tourist hotels or, potentially, an eventual export market if handling and processing hygiene can be significantly improved.

Figure 5.  Average Fecal Coliforms, 15 Tanbi & Western Region sites 2010 – 2013.

Figure 6.  Average Fecal Coliforms at inside Tanbi sites Jan. – Sept. 2013

Since January 2012, the Department of Water Resources in partnership with other Gambian government agencies and TRY have conducted sanitary shoreline surveys in these oyster harvesting estuaries with training and support from the USAID/BaNafaa Project to identify potential sources of contamination.

In early January 2014, significant progress was made as Dr. Michael Rice of URI trained and worked with a group of eight resource persons from 5 Gambian agencies to analyze the three years of water quality data & sanitary shoreline survey observations.  The result of the analysis was to assign provisional water quality zones and classifications for three estuaries (Tanbi, Kubuneh and Allahein).  The water quality classification zones were mapped using the Geographic Information System services of the Gambia National Environment Agency (NEA).  The results are shown in Figure 7 below.

Figure 7.  Provisional Water Quality Classification Zones for Shellfish Harvesting

These results and the provisional classification zones were shared with TRY Association members and stakeholders at the Second Annual Oyster and Cockle Co-Management Plan Review meeting on January 16th.  The provisionally prohibited zones (in red) were of particular concern to all and drew attention to the need to focus efforts on addressing the causes of poor water quality in these areas.  Stakeholders also noted that the timing of the 8 month closed season for harvesting of oysters that is already in place as a management measure under the Co-Management Plan for the Tanbi coincides with the recommended seasonal closure based on water quality data (yellow areas on the map).

This classification and mapping of water quality zones is the basis for a Gambian National Shellfish Sanitation Plan (GNSSP) that is in initial draft form and still under development.  Continuation of the process for developing the GNSSP as the USAID/BaNafaa Project ends will be formalized in a multi-agency Memorandum of Understanding that is expected to be signed in April.  It will formalize engagement of the participating agencies in continued investment of human and financial resources for this effort.  Recommendations of USAID/BaNafaa and the Gambian stakeholders on the way forward for the development and implementation of the GNSSP include the following:

- Continued water quality monitoring at shellfish harvesting sites

- Continued sanitary shoreline surveys

- Behavior change towards the application of the principles of hygiene and sanitation

- Application of good manufacturing practices (GMPs) and good hygiene practices (GHPs)

- Strengthening and formalization of interagency collaboration.

Finalizing and implementing a GNSSP will make The Gambia second to only one other country in Sub-Saharan Africa that has such a plan – South Africa.  For this reason, it will serve as a point of reference and an important case study for developing countries striving to sustainably manage their shellfisheries by improving the quality and the value of their product. Dr. Rice shared the process in a presentation at the 34th Milford Aquaculture Seminar in February 2014.

- Next Steps in the Allahein River Estuary Bi-lateral Oyster and Cockle Co-Management Planning Process

Field Visit to Southern Senegal.  In early January 2014, the TRY Coordinator (Fatou Janha Mboob), the TRY Secretary (Isatou Jarjue) and two Department of Fisheries staff (Ebrima Jabang and Kanyi Babanding) conducted a three day transboundary visit to five Southern Senegal oyster and cockle harvesting communities in the Allahein River estuary to follow up on previous joint management planning meetings.  The communities included Niafrang, Kabajo, Abene, Katak, and Donbondir.  All the communities showed interest in the sustainable management of oyster and cockle fishery in the Allahein River estuary. They all acknowledged that the shared stock of oyster and cockle requires an ecosystem-based, co-management strategy for their benefit and the benefit of future generations. The communities agreed to collaborate with TRY to hold future meetings and reach consensus on management measures, bye laws and conservation of the mangrove ecosystem.  The TRY/DoFish delegation also visited the Department of Fisheries in Abene and was assured of their collaboration for the preparation of a Joint Transboundary Co Management Plan.  In Donbondir, the delegation also had the opportunity to meet the Senegalese Government National Assembly Member for the region.  She pledged support and collaboration for the joint co-management effort.

Figure 8.  TRY delegation meeting with the Kabajo oyster harvesting community in Southern Senegal to discuss transboundary management planning in the Allahein River estuary

Joint Meeting in Kartong.   Following the trip to Southern Senegal, the Allahein Kafoo (the name given to the group of Gambian and Senegalese shellfish harvesting communities operating in the Allahein River estuary) conducted a meeting in Kartong.  Six Senegalese and two Gambian communities attended.  Discussion centered on the environmental issues at stake and on the organizational principles and structure of TRY and its member communities that could be adapted to the context of the Southern Senegal shellfish harvesting communities in the Allahein.  The Senegalese participants identified next steps, including the need to sensitize their community members further and to organize their own association(s).  Having representative structures in place on the Senegal side will facilitate joint discussion and planning with TRY and other stakeholders.

Figure 9.  Joint meeting of Gambian and Southern Senegal shellfish harvesting communities in Kartong to discuss joint transboundary management planning in the Allahein River estuary.

Based on the extremely positive momentum that USAID/BaNafaa supported outreach has generated to date, in November 2013, URI/CRC submitted a concept note to the US State Department through the U.S. Embassy in Banjul proposing post-USAID/BaNafaa support to TRY for continued development of this transboundary plan.  URI will continue to follow up with the Embassy and USAID.

### 2.1.3   Water, Sanitation and Hygiene (WASH)

The USAID/BaNafaa Project was awarded a Water and Sanitation (WASH) add-on at the end of Year 2 to support needed water supply and sanitation improvements at approximately seven public sole fishery and oyster/cockle fishery landing/processing sites by April 2014.  Six fish and oyster landing sites were prioritized for WASH interventions as a result of the needs assessment and stakeholder workshop conducted in Year 3 (FY12).  In December 2013, WASH Management Plans were signed and 5 toilet blocks and 5 water points were handed over to communities at three of the six sites, Old Jeshwang (consisting of a fish landing and an oyster harvesting site), Brufut (fish landing site with 2 toilet blocks and 2 water points due to the distance from one end of the site to the other) and Kamalo (oyster harvesting site).

In March, 2014 an additional 2 WASH Management Plans were signed and 2 sanitation blocks and 2 water points were handed over at the Kartong fish landing and oyster harvesting sites.

As a result, a total of 11,663 people have improved access to water and sanitation.  Direct beneficiaries include fishermen, oyster harvesters, women fish venders, small scale fish processers and other laborers that utilize these facilities daily as well as the general public. The clean water supply and sanitary facilities at these sites will also contribute to improved water quality in the marine and estuarine environments in the immediate vicinity, as well as the sanitary handling of the seafood supply landed and processed at the sites and destined for local and export markets.

The WASH Management Plan signing and facilities handover event at Kartong is pictured in Figures 10 – 14 below.  Attendees included, the Minister of Fisheries and Water Resources, The Charge d’Affairs of the U.S. Embassy, Ambassador Michael Arietti, The U.S. Embassy Deputy Chief of Mission, The University of Rhode Island/Coastal Resources Center, The USAID/BaNafaa Project Manager/WASH Coordinator, The Director of the Department of Fisheries, TRY, NASCOM, the CEO of GAMWORKS, the Director of Tarud, the Director of the National Environment Agency, local elected officials, the media, Southern Senegal Allahein River estuary oyster community representatives and many others.  Speakers noted that improved sanitation and hygiene is of particular importance at this site, which is an international border crossing between Southern Senegal and The Gambia.

The fish and oyster communities at Kartong were particularly pleased with the WASH facilities and in particular the water points.  The Kartong sites could not be easily linked to the municipal water supply due to the isolation of the sites.  Establishing a borehole was also a challenge due to proximity to the shoreline and the vulnerability to salinization, especially when considering climate change issues of sea level rise and coastal erosion over the medium to long term.  Separate protected wells located 250 - 500 meters distant from the sites were established as the most climate friendly and sustainable solution to water supply at these sites.

Figure 10.  Kartong TRY Association members welcoming their elders to the WASH handover ceremony

Figures 11 and 12.  Ribbon cutting, handover and inspection by the public of toilet facilities at the 2 Kartong sites (oyster site at left and fishing site at right)

Figures 13 and 14.  (from left behind the tap) The U.S. Embassy Charge d’Affairs, the President of the Kartong Fish landing site WASH Committee (the woman) and the CEO of GAMWORKS test the new water point.  Solar powered pumping and storage system for the protected well that supplies the water point located 500 meters away.

The signed WASH Management Plans, validated at a stakeholder meeting in November, identify WASH Management Committees as the governance structure that will lead behavior change efforts and manage daily operations, as well as short and long term maintenance and sustainability of the facilities.  The plans ban open defecation (with monetary penalties) and set user fees for water, toilet and shower use.  They also assign roles and responsibilities within the landing site community and between the landing site, local authorities and other government agencies and partners.  In Quarter 2 (January), USAID/BaNafaa’s Administrative/Finance Assistant provided hands-on financial management training to 40 participants from WASH Management Committees, DoFish landing site field staff at the 6 WASH sites and supervisory DoFish staff in Banjul to reinforce the specific procedures and skills needed to make this scheme a success.  The project is also assisting WASH Management Committees to register and open their bank accounts and is providing an initial supply of color coded receipt books for user fees.

This quarter Participatory Hygiene and Sanitation Transformation (PHAST) training, Training of Trainers in hygiene promotion and outreach, and fish handling and hygiene training was conducted at the two remaining WASH sites – Tanji and Sanyang fish landing sites.  A total of 80 participants were trained per site.

Table 2. WASH Sites and Activities Status as of March 31, 2014

|  | Site | Type | Comments |
| --- | --- | --- | --- |
| 1 | Brufut | Fisheries | Training, Management Plan and Facilities complete. Handed over December 2013. Hygiene promotion outreach on-going. |
| 2 | Kamalo | Oysters | Training, Management Plan and Facilities complete and handed over December 2013. Hygiene promotion outreach on-going. |
| 3 | Sanyang | Fisheries | Training completed. Management Plan and facilities to be completed by end April 2014. Sanitary facilities only. The site has water. |
| 4 | Old Jeshwang | Fisheries & Oysters | Training, Management Plans and Facilities complete and handed over December 2013. Hygiene promotion outreach on-going. |
| 6 | Kartong | Fisheries & Oysters | Training, Management Plan and Facilities complete and handed over March 2014. Hygiene promotion outreach on-going |
| 7 | Tanji | Fisheries | Training completed. Management Plan and facilities to be completed by end April 2014. Sanitary facilities only. The site has water. |

Lessons learned and challenges faced this quarter for completion of the 2 remaining sites, Tanji and Sanyang include the following:

- The subaward to GAMWORKS for design, quality control and oversight of construction, as well as the contracting and management of contractors to do the work was a successful approach. As the CEO of GAMWORKS articulated in his public remarks at the Kartong WASH handover ceremony, this project did not require troubleshooting at his level as most projects do.  The USAID/BaNafaa WASH Coordinator and the GAMWORKS Project Manager worked very effectively together and GAMWORKS exhibited a high level of flexibility and patience in accompanying the project’s participatory process.  USAID/BaNafaa likewise noted that feedback received from communities about the quality of work done on the WASH facilities, as well as the conduct of GAMWORKS and its contractors during construction, were very positive.  This is not always the case with construction activities that bring in outside workers and temporarily disrupt the physical environment.

- Construction of the Tanji and Sanyang WASH facilities was unexpectedly delayed due to closure of the border between Senegal and The Gambia to commercial trucking during the quarter.  Basalt stones imported from Senegal needed for the concrete was, therefore, not available.  Finally, GAMWORKS decided to use washed laterite as the second best option (see Figure 15 below).  This also required increasing the concentration of cement in the mixture.

Progress on construction of the Tanji and Sanyang toilet facilities is now advancing rapidly and will be completed in April.  See Figures 16 and 17 below.

Figure 15. At left, washed laterite used in place of basalt stones for the concrete mixture due to border closures cutting off the basalt supply from Senegal.

Figure 16.  Progress on construction of the Tanji fish landing site toilet facility as of March 26th.

Figure 17.  Members of the Sanyang fish landing site WASH Management Committee in front of the nearly completed toilet facility.

## 2.2 Intermediate Result 2:

Year 5, Quarter 2 Highlights

- NASCOM capacity strengthened (see IR1)

- TRY Oyster Women’s Association capacity strengthened. (see IR1)

- WASH and GNSSP institutional actors capacity strengthened (see IR1)

- 246 people trained since October 2013 (this fiscal year).  A total of 1,962 people trained over the life of the project, 69% of them women.

- End of project stakeholder review and closeout workshop conducted.  Way forward priorities identified.

Institutional capacity strengthened at all levels of governance to implement an ecosystem-based, co-management approach to sustainable fisheries, and to prevent overfishing.

### 2.2.1	End of Project Stakeholder Review and Closeout Workshop.

The USAID/BaNafaa Project Closeout Workshop was a day-long event conducted on March 27th.  Seventy-nine participants (45 male and 34 female) from 25 organizations attended.  The Minister of Fisheries and Water Resources had attended the Kartong WASH handover event the previous day, but with the Director of Fisheries had to travel on the 27th.  They were represented by the Minister of Youth and Sports and the Deputy Director of Fisheries respectively.  The Charge d’Affairs of the U.S. Embassy also spoke at the opening ceremony, which was facilitated by the USAID/BaNafaa Project Manager/WASH Coordinator.   The WWF-WAMPO Coordinator based in Dakar was also present.

Figure 18.  The TRY Coordinator facilitates a discussion of TRY achievements in partnership with the USAID/BaNafaa Project

Opening remarks highlighted the concept that the end of the USAID/BaNafaa project represents the beginning of a new phase of engagement for Gambian stakeholders to take the lead in continuing and expanding upon the sustainable fisheries management efforts developed so successfully with the assistance of the project.

Sessions focused on a review of the process and actions undertaken over the last five years, the results and the factors of success.  Enabling conditions in place prior to USAID/BaNafaa Project start-up in 2009 were also highlighted as follows:

- A favorable legal framework:  The Gambia is the only country in West Africa that as of 2007 had enacted a fisheries legislation that makes it possible to adopt and implement a fisheries co-management plan under the Ecosystem-Based Fisheries Management (EBFM) approach.

- The founding of TRY Oyster Women’s Association in 2007.

- The commissioning by GAMFIDA of a Marine Stewardship Council pre-assessment of the Gambian sole fishery in 2007.

Figure 19.  Workshop participants listen to an intervention.  A timeline of project activities and achievements encircles the room on the walls.

One of the most powerful sessions was the personal testimony of stakeholders and beneficiaries.  A few examples are as follows:

- Kadiatou Jallow, Brufut landing site artisanal fish processor and officer of NASCOM, spoke about how she has an education and how education is not only good for office jobs.  Her education has enabled her to be a strong leader in the fish processing and drying business that she inherited from her mother.  She is able to read and write and apply knowledge gained from working with initiatives like the USAID/BaNafaa Project to make a difference in her community and for the sustainability of fisheries livelihoods, “My knife is my pen…”

- Eliman Sarr, President of NASCOM shared that fishermen from Barra on the north bank of the mouth of the Gambia River, where the closed area designated under the Sole Co-Management Plan does not reach, have seen the size of lobsters and other fish harvested this year after the 4 months 1 nautical mile closed area was implemented and enforced.  They too want to have their area included in the closure and implement the other management measures in the plan.  This feedback demonstrates the value of the ecosystem approach, as the measures implemented for the sole fishery are perceived by fisherfolk to have visible, positive impact on a range of species of value and on the ecosystem as a whole.

- Isatou Jarjue, TRY Kartong, explained how the oyster women now know who they are.  They know what we are doing and why.  They protect the mangroves and the mangroves are the bank of the fisheries.  Likewise, the oyster women are the bank of the fisheries.  Their actions protect the mangroves and the fisheries for themselves and for everyone.

Short, medium and longer term way forward priorities identified by workshop participants include the following:

- A typographical error in the gazetted version of the sole co-management plan meant to define the 9 nautical mile exclusive use zone for NASCOM for the sole fishery should be immediately corrected.

- Sole Fishery Stock Assessment should be updated annually.  The data collection protocol agreed to by DoFish in December 2013 must be implemented immediately as April (marking the last month before the 1 nautical mile closed season begins) is a critical data collection period.

- Another MSC pre-assessment of the sole fishery should be conducted as soon as possible to identify and better focus efforts on the remaining gaps.  Eventual full certification should be sought.  Eventual certification of processors for traceability standards and use of the eco-label to market Gambian sole should be pursued.

- A joint framework for the sustainable management of the sole stock shared between The Gambia and Senegal should be put in place. This is also critical for MSC certification.

- Continued support for annual bi-lateral co-management meetings is critical.

- Expansion of sole and marine catfish co-management to additional areas and communities in The Gambia should be undertaken.

- Institutional capacity development of NASCOM and LACOMS.

- Development of a Cabinet Paper based on the Cost Comparison study of the sole fishery between Gambia and Senegal should be pursued.  It was planned for Year 5 of the USAID/BaNafaa project, but not completed.

- Expansion of oyster and cockle co-management to additional areas and communities in The Gambia should be undertaken.

- Approval of a joint co-management plan for oysters and cockles in the Allahein River Estuary should be achieved.

- Approval of a GNSSP and its sustainable implementation should be supported and achieved.

- Institutional capacity development of TRY is critical.  TRY should be supported to establish its own shellfish processing and education center, including acquisition of land and construction of the center.

- DoFish should include assessment of the stock of the “invisible fishery” in its regular fisheries statistics collection analysis and reporting.

- Government stakeholder institutions should support WASH Management Committees to manage WASH activities and facilities sustainably.

- Unmet WASH needs at additional fisheries landing and oyster harvesting sites should be addressed.

The Final USAID/BaNafaa Project Report following project closure at the end of April will cover lessons learned, sustainability and the way forward in more detail.

## 2.3  Intermediate Results 3 and 4:

Nursery areas and spawning areas for critical life stages of commercially important species and for associated marine turtles and mammals are protected

Year 5, Quarter 2 Highlights

Implementation of the Fishery Co-Management Plan for The Gambia Sole Complex (see IR1).

- 121,245 ha under improved management (the entire Atlantic Coast of The Gambia out to 9 nm)

- Seasonal closure for all species and gear types out to 1 nautical mile from May to October

- Fish size limits and gear restrictions.

- Amendment to increase mesh size limits from the current 80mm to 92mm and to integrate marine Catfish signed in December 2013.

Implementation of Oyster and Cockle Fishery Co-Management Plan for the Tanbi Special Management Area (see IR1).

  - 6,304 ha under improved management (the entire Tanbi Wetlands National Park)

  - Seasonal Closure for Oysters from July to February (8 months)

  - Gear restrictions for mangrove protection

  - Mangrove reforestation

  - Shellfish size limits

  - Shellfish Sanitation Planning, including bi-weekly water quality testing , bi-annual shoreline sanitation surveys and provisional water quality classification zones identified and mapped.

Improved biophysical conditions in areas under improved management not yet demonstrated.

Change unsustainable and destructive marine resource use practices that threaten improved biodiversity conservation in the West Africa Marine Ecoregion.

# 3.	Project Management

In-country project management has been taken over by Dr. Bamba Banja, the USAID/BaNafaa WASH Coordinator following the passing of the Project Manager, Mr. Ousman Drammeh.  As planned, the WWF-WAMPO sub-contract ended on December 31, 2013.  Two DoFish staff seconded to WWF for the duration of the project, Kanyi Babanding and Gibril Gabis, have returned to DoFish as of January 1, 2014.

In January 2014, URI/CRC submitted and USAID approved the closeout plan for the project and the proposed disposition of property.  URI has undertaken the paperwork for the transfers, which will be finalized in April.

At the end of March the USAID BaNafaa team and URI debriefed with the Minister of Fisheries and Water Resources and the Department of Fisheries.  Exit interviews were conducted with project implementing partners, WWF, GAMWORKS, TARUD, TRY and NASCOM as well as with the two URI staff.

## 3.1 International Travel Schedule

This international travel schedule does not include travel between The Gambia and Senegal, which for planning and management purposes is considered local travel. The following list captures all international travel other than within and between The Gambia and Senegal.

First Quarter Actual

- Kathy Castro:  (November 2013) Prepared and participated in the 2nd Annual Bi-Lateral Co-Management Meeting in The Gambia and the 2nd Annual Sole Co-Management Plan Review Meeting.  TA to DoFish on sustainability of stock assessment.

- Karen Kent:  (December 2013) WASH handover event and follow-up of actions recommended at the November meetings.

Second Quarter Actual

- Mike Rice:  (January 2014) Gambian National Shellfish Sanitation Plan training, MOU signing and TA. Participation in TRY annual Cockle and Oyster Co-Management Plan review meeting.

- Karen Kent:   (March/April 2014) WASH handover and Project Review and Closeout meeting with stakeholders.

- Cindy Moreau:  (March/April 2014) Project Closeout.

## 3.2 Environmental Monitoring and Compliance

Based on the revised initial environmental evaluation (IEE) approved in 2011 for the project, an Environmental Monitoring and Mitigation Plan is in place to ensure no significant environmental impacts are occurring for those actions identified in the IEE with a negative determination subject to conditions.  Activities conducted this quarter that have conditions and require monitoring and/or mitigation plans include:

- Fisheries management plans

- WASH improvements at landing sites

Status on these activities will be included in the Environmental Monitoring and Mitigation Report submitted to USAID with the USAID/BaNafaa  Final Report for the period through April 2014.

## 3.3 Branding

The USAID/BaNafaa Project provides information through many existing channels. This includes through presentations at meetings, conferences, outreach sessions and other forums as well as through print media—e.g.,  peer-reviewed articles in professional journals, locally produced Information, Education and Communication (IEC) materials, pamphlets, brochures, policy briefs, guides, and PowerPoint presentations. The main target audiences include local communities, local government agencies, national policymakers, grassroots NGOs, and other donors. Acknowledgement is always given to the generous support of the American people through USAID in all Project communications and materials. Also recognized are partnerships and support from local government ministries, agencies and departments who participate in various activities of the Project.

Synopsis of Planned Communication Items Affected by USAID Marking/Branding Regulations (ADS 320/AAPD 05-11)

| Item | Type of USAID marking | Marking Code | Locations affected/ Explanation for any ‘U’ |
| --- | --- | --- | --- |
| Press materials to announce Project progress and success stories | USAID logo (co-branded as appropriate) | M | Primarily a Gambian audience |
| Project brief / fact sheet | USAID logo (co-branded as appropriate) | M | Primarily a Gambian audience |
| PowerPoint presentations at meetings, workshops and trainings | USAID logo (co-branded as appropriate) | M | Primarily a Gambian audience |
| Brochures/posters on environmental issues | USAID logo (cobranded where/as appropriate) | M | Primarily a Gambian audience |
| Landing or marketing site facility improvements | USAID logo / stickers (cobranded where/as appropriate) | M | Primarily a Gambian audience |
| Project Office/room within WWF/Gambia office in Banjul | Project sign in English and local dialect name as well (USAID/BaNafaa) but no USAID identity used | M | Primarily a Gambian audience |
| CRC Project Office/room within TRY/Gambia office in Banjul | Project sign in English and local dialect name as well (USAID/BaNafaa) but no USAID identity used | M | Primarily a Gambian audience |
| Fisheries management plans |  | PE | Primarily a Gambian audience |
| Project vehicles, office furnishings and computer equipment purchased for project administration. | No USAID identity used | U | Standard exclusions under USAID marking guidelines/policies |

Marking Codes:  M = Marked, U=Unmarked, PE = Presumptive Exception, W=Waiver

## 3.4 TraiNet Data on Trainings Conducted during the Reporting Period

The Ba Nafaa Project Office compiles information on all training events as required by USAID, This information is submitted to CRC where the data is entered into the TraiNet electronic reporting system. A summary of trainings conducted to date is provided in the following table.

| Training program | Location | Start date | End date | Participants |  |  | Estimated Cost |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Male | Fem | Total | US $ |
| Study Tour to Sine Saloum | Senegal | 12/16/2009 | 12/18/2009 | 1 | 31 | 32 | 3,507 |
| Co-management Training on Sole Fishery | The Gambia | 1/25/2010 | 01/26/2010 | 37 | 3 | 40 | 2,188 |
| Co-management Training on the Oyster Fishery | The Gambia | 02/01/2010 | 02/02/2010 | 2 | 51 | 53 | 2,373 |
| Aquaculture training | The Gambia | 01/12/2010 | 02/05/2010 | 60 | 0 | 60 | 2,696 |
| Training on Entrepreneurship (study tour to Baddibu) | Gambia | 03/18/2010 | 03/19/2010 | 2 | 11 | 13 | 600 |
| Stock assessment training | The Gambia | 03/15/2010 | 03/22/2010 | 14 | 5 | 19 | 3,144 |
| Training on Improved Processing & Packaging | Gambia | 30/4/2010 | 12/4/2010 | 0 | 300 | 300 | 750 |
| Coastal Adaptation to Climate Change | US | 4/6/2010 | 25/6/2010 | 2 | 0 | 2 | 26,000 |
| Cayar Study Tour | Senegal | 13/6/2010 | 18/6/2010 | 11 | 4 | 15 | 4,500 |
| Oyster Aquaculture Training | Gambia | 17/6/2010- | 28/6/2010 | 1 | 36 | 37 | 750 |
| Water Quality Assessment Training Workshop | Gambia | 23/6/2010 | 23/6/2010 | 18 | 5 | 23 | 100 |
| Fisheries Leadership | US | 16/8/2010 | 3/9/2010 | 3 | 1 | 4 | 32,000 |
| Biostatistics course | Gambia | 09/20/2010 | 09/27/2010 | 10 | 2 | 12 | 5,832 |
| GRAND TOTAL YEAR 1 |  |  |  | 161 | 449 | 610 | $84,440 |
| Micro-credit and enterprise development | Gambia | 25/10/2010 | 2/11/2010. | 0 | 250 | 250 | 1,290 |
| Climate Change workshop | Senegal | 3/22/2011 | 3/25/2011 | 52 | 8 | 60 | 50,900 |
| Study tour to Tanzania on res. mgt and livelihood development | Tanzania | 2/7/2011 | 2/12/2011 | 0 | 1 | 1 | 2,145 |
| Water quality and shellfish sanitation | USA | 5/21/2011 | 6/5/2011 | 3 | 0 | 3 | 15,910 |
| Fish stock assessment | USA | 5/21/2011 | 6/12/2011 | 3 | 2 | 5 | 34,387 |
| MPA-PRO Certification Training | Kenya | 6/13/2011 | 6/17/2011 | 1 | 0 | 1 | 3,000 |
| BS Degree Training – Fisheries technology | Nigeria | 5/15/2011 | 8/16/2013 | 1 | 0 | 1 | 10,000 |
| BS Degree Training – Fisheries technology | Nigeria | 8/29/2011 | 9/30/2012 | 1 | 0 | 1 | 10,000 |
| TRY members to FENAGIE | Senegal | 09/11/2011 | 9/15/2011 | 0 | 4 | 4 | 2,759 |
| GRAND TOTAL YEAR 2 |  |  |  | 61 | 265 | 326 | 130,391 |
| CUMULATIVE GRAND TOTAL TO DATE END YEAR 2 |  |  |  | 222 | 714 | 936 | $214,831 |
| PHE workshop | Senegal | 12/4/2011 | 12/07/2011 | 0 | 1 | 1 | 1,174 |
| Training of the Facilitators for WASH Needs Assessment | The Gambia | 12/27/2011 | 12/29/2011 | 8 | 2 | 10 | 1,128 |
| TRY literacy training | The Gambia | 11/2011 | On-going | 0 | 30 | 30 | TBD |
| Shellfish Sanitation Shoreline Survey Training | The Gambia | 1/5/12 | 1/11/12 | 8 | 0 | 8 | TBD |
| Shellfish Sanitation Shoreline Survey Training | The Gambia | 1/16/12 | 1/16/12 | 25 | 5 | 30 | 945 |
| USAID Environmental Compliance Training | Ghana | 3/19//12 | 3/23/12 | 1 | 0 | 1 | 2,075 |
| Stock Assessment | The Gambia | 1/20/2012 | 09/30/2012 | 2 | 0 | 2 | 4,098 |
| TRY Microfinance training | The Gambia | 2/6/12 | 2/24/12 | 0 | 67 | 67 | 1,229 |
| TRY hygiene/food handling training | The Gambia | 1/31/12 | 2/1/12 | 0 | 90 | 90 | 343 |
| Bi-lateral Climate Change Vulnerability Assessment Workshop | The Gambia | 4/10/2012 | 4/11/2012 | 35 | 9 | 44 | 27,651 |
| WASH Needs Assessment Stakeholder Workshop | The Gambia | 4/18/2012 | 4/18/2012 | 25 | 13 | 38 | 961 |
| Shellfish Sanitary Shoreline Survey Report Stakeholder Workshop | The Gambia | 4/19/2012 | 4/19/2012 | 17 | 4 | 21 | 775 |
| Bi-lateral Fisheries Co-Management Workshop | The Gambia | 5/30/2012 | 5/31/2012 | 60 | 25 | 85 | 23,110 |
| Population, Health Environment URI/Summer Institute | USA, Rhode Island | 6/4/2012 | 6/22/2012 | 2 | 0 | 2 | 12,430 |
| Fisheries Leadership | USA, Rhode Island | 7/2/2012 | 7/20/2012 | 2 | 1 | 3 | 19,516 |
| GRAND TOTAL YEAR 3 |  |  |  | 186 | 247 | 433 |  |
| CUMULATIVE GRAND TOTAL TO DATE END YEAR 3 |  |  |  | 408 | 961 | 1369 |  |
| Administrative/Finance Training | The Gambia | 11/12/2012 | 11/14/2012 | 6 | 3 | 9 | 947 |
| PHAST Training (Brufut) | The Gambia | 11/27/2012 | 11/29/2012 | 16 | 24 | 40 | 1,426 |
| PHAST Training (Old Jeshwang) | The Gambia | 12/17/2012 | 12/19/2012 | 9 | 31 | 40 | 1,393 |
| PHAST Training (Kartong) | The Gambia | 01/7/2013 | 01/09/2013 | 5 | 35 | 40 | $1393 |
| PHAST training (Kamalo) | The Gambia | 01/21/13 | 01/23/2013 | 0 | 40 | 40 | $1393 |
| Administrative/Finance Training follow-up | The Gambia | 03/18/2013 | 03/18/2013 | 5 | 3 | 8 | $280 |
| WASH TOT – Community Outreach and Hygiene Promotion - Brufut | The Gambia | 04/17/13 | 04/19/13 | 10 | 10 | 20 | $877 |
| WASH TOT – Community Outreach and Hygiene Promotion - Kartong | The Gambia | 04/23/13 | 04/23/13 | 4 | 16 | 20 | $877 |
| WASH TOT – Community Outreach and Hygiene Promotion - Old Jeshwang | The Gambia | 04/30/13 | 05/02/13 | 5 | 15 | 20 | $877 |
| WASH TOT – Community Outreach and Hygiene Promotion - Kamallo | The Gambia | 05/15/13 | 05/17/13 | 0 | 20 | 20 | $877 |
| Fish Biology Course | The Gambia | 03/01/13 | 04/16/13 | 6 | 5 | 10 | $786 |
| WASH Sites Fish handling and hygiene - Brufut | The Gambia | 8/17/2013 | 8/19/2013 | 10 | 10 | 20 | $698 |
| WASH Sites Fish handling and hygiene Jeshwang | The Gambia | 7/29/2013 | 7/31/2013 | 3 | 17 | 20 | $698 |
| WASH Sites Fish handling and hygiene - Kamalo | The Gambia | 8/1/2013 | 8/3/2013 | 0 | 20 | 20 | $698 |
| WASH Sites Fish handling and hygiene - Kartong | The Gambia | 8/14/2013 | 8/16/2013 | 2 | 18 | 20 | $698 |
| GRAND TOTAL YEAR 4 |  |  |  | 81 | 266 | 347 |  |
| CUMULATIVE GRAND TOTAL TO DATE END YEAR 4 |  |  |  | 489 | 1227 | 1716 |  |
| Bi-lateral Co-Management Workshop | The Gambia | 11/11/2013 | 11/11/2013 | 28 | 10 | 38 | $15,793 |
| PHAST Training Tanji | The Gambia | 1/17/14 | 1/19/2014 | 21 | 19 | 40 | $1,164 |
| WASH supervision and Management Committee Admin./Fin. Training | The Gambia | 1/24/2014 | 1/24/2014 | 10 | 30 | 40 | $881 @ 35.47 |
| PHAST Training Sanyang | The Gambia | 1/31/2014 | 2/2/2014 | 23 | 17 | 40 | $1,164 |
| WASH TOT – Community Outreach and Hygiene Promotion - Sanyang | The Gambia | 2/5/2014 | 2/7/2014 | 7 | 13 | 20 | $741 |
| WASH TOT – Community Outreach and Hygiene Promotion - Tanji | The Gambia | 2/9/2014 | 2/11/2014 | 7 | 13 | 20 | $741 |
| WASH Sites Fish handling and hygiene Sanyang | The Gambia | 2/14/2014 | 2/16/2014 | 9 | 11 | 20 | $741 |
| WASH Sites Fish handling and hygiene Tanji | The Gambia | 3/5/2014 | 3/7/2014 | 7 | 13 | 20 | $741 |
| Water quality zone mapping | The Gambia | January 2014 |  | 8 | 0 | 8 | TBD |
| GRAND TOTAL YEAR 5 |  |  |  | 120 | 126 | 246 |  |
| CUMULATIVE GRAND TOTAL TO DATE END YEAR 5 |  |  |  | 609 | 1353 | 1962 |  |

## 3.5 Estimated Financial Status

The following table shows a pipeline analysis of expenditures in relation to obligations through March 31, 2014.

| AMOUNT SUB-OBLIGATED |  | 3,414,566.00 |
| --- | --- | --- |
| (total federal outlays as of last SF 425/voucher) |  |  |
| Expenditures |  |  |
| Period Covered In Last SF 425 | Thru December 2013 | 3,132,244.21 |
|  | Jan - March 2014 | 196,699.00 |
| TOTAL EXPENDITURES (Amt on SF 425 + Recent Expenditure) |  | $3,328,943.21 |
| BALANCE OF SUB-OBLIGATED FUNDS REMAINING |  | $85,621.30 |

Note that URI/CRC estimates that the remaining balance of sub-obligated funds will be spent by April 30, 2014, the project end date.

# Appendix A. Results Framework & Life-of-Project (LOP) Targets

The Project Results Framework below is organized by Project Goal and IR. The Gambia - Senegal Sustainable Fisheries Project contributes directly to USAID West Africa Regional Office’s Environment & Climate Change Response (ROECCR) Results Framework, specifically IRs 1, 3 and 4 as per the May 2011 draft below.  Each IR in the Gambia - Senegal Sustainable Fisheries Project Results Framework has one or more indicators and LoP Targets that are shown in the table on the following pages.  Indicators were harmonized and reduced in number in the Year 4 workplan to reflect USAID Standard Indicators.

GOAL

Artisanal fisheries ecosystems in The Gambia and selected stocks shared with Senegal are being managed more sustainably, incorporating significant participation of fisheries stakeholders, and attaining improved economic benefits for both male and female stakeholders in the market value chain

IR 2: Institutional capacity strengthened at all levels of governance to implement an ecosystem-based, co-management approach to sustainable fisheries, and to prevent overfishing

IR 4: Change unsustainable and destructive marine resource use practices that threaten improved biodiversity conservation in the West Africa Marine Ecoregion

IR 1: Strategies to increase social and economic benefits to artisanal fishing communities, and otherwise create incentives for a sustainable fisheries agenda in the WAMER identified, tested and applied

IR 3: Nursery areas and spawning areas for critical life stages of commercially important species and for associated marine turtles and mammals are protected

|  | Indicator | LOP Targets | Comments |
| --- | --- | --- | --- |
| IR 1 |  |  |  |
| 2 | No people with increased economic benefits derived from sustainable natural resource management and conservation as a result of USG assistance (ROECCR 2.1.1) | 220 | Does not control for double counting of the same individuals if they received assistance (i.e., training) that improves their economic benefits on multiple occasions. Original LOP was significantly underestimated. |
| W1a | No of people with improved access to sanitation facilities | 23,175 | Adjusted from Year 3 target of 56,000 and Year 4 target of 20,000. |
| W1b | No of people with improved access to water facilities | 11,663 | Separated from sanitation and adjusted from Year 3 target of 56,000 and Year 4 target of 20,000. |
| W2 | Number of persons receiving Participatory Hygiene and Sanitation Transformation (PHAST) Training. | 240 | 40/site x 6 sites = 240 |
| W3 | Number of persons receiving training and outreach messages on hygiene promotion | 6000 | 1000/site x 6 sites = 6000 |
| W4 | Community water and sanitation committees established and trained with program assistance | 6 | Original estimate based on 6 sites. Two sites (Old Jeshwang and Kartong) have both a fishery and an oyster harvesting community. Each have separate WASH facilities and a WASH Management Committee. Total committees will be 8. |
| IR 2 |  |  |  |
| 4 | No of institutions with improved capacity to address NR, BD, climate change, water issues as a result of USG assistance (ROECCR 4.1.1) | 13 | Does not include those reported under CC3. Does not double count the same institution receiving multiple capacity strengthening interventions. |
| 5 | Number of people receiving USG supported training in natural resources management and/or biodiversity conservation. (F 4.8.1-27) | 1958 (gender disaggregated) | = Trainet. Does not control for double counting of the same individuals receiving multiple trainings. Original LOP of 200 was a significant underestimate. LOP now est. at 1,958. |
| 6 | Improvements on a governance scorecard covering, goals, constituencies, commitment and capacity dimensions, including measures that legislation and regulations are being implemented and complied with, and budgetary investments by government in fisheries management | Qualitative increases on score card criteria for Gambia EB-fisheries mgt |  |
| 11 | Number of laws, policies, strategies, plans, agreements, or regulations addressing climate change (mitigation or adaptation) and/or biodiversity conservation officially proposed, adopted, or implemented as a result of USG assistance (ROECCR 4.3.1) | 2 |  |
| CC1 | Number of climate vulnerability assessments conducted as a result of USG assistance | 1 |  |
| CC2 | Number of stakeholders using climate information in their decision making as a result of USG assistance | 30 | = number of participants at the vulnerability assessment workshop as the workshop prioritized actions for an adaptation proposal based on analysis of VA findings. |
| CC3 | Number of institutions with improved capacity to address climate change issues as a result of USG assistance | 8 | = number of institutions at the CCVA Workshop. |
| IR 3 & 4 |  |  |  |
| 12 | No. of Hectares in areas of biological significance under improved natural resource management (ROECCR 1.1): - Hectares covered by the fisheries management plan defined as the range of fishing fleets targeting these species - Oyster fishery estuarine and mangrove areas designated and allocated as community managed zones, including no-take areas | FMP Areas: - Sole = 12nm seaward = 158,332 ha Community managed oyster zones: - Tanbi wetlands 6000 ha | Original estimate for Sole was based on 12nm seaward as per the artisanal fishing zone specified in the Fisheries Act of 2007. The final Sole co-management plan limited the special management area with user rights for NASCOM out to 9nm. So, total hectares for Sole are 121,245. |
| GOAL |  |  |  |
| 17 | No. of HA in areas of biological significance showing improved biophysical conditions as a result of USG assistance. (ROECCR AO1) = Hectares under effective mgt (progress towards BRPs) for sole and oysters | No targets set but progress towards BRPs will be tracked. |  |

Results to Date and Year 5 (FY 14) Quarter 2 Results

| No | Indicator | Cumulative Results (as of FY13) | FY14 Target | Q1 | Q2 | LOP Target | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | No people with increased economic benefits derived from sustainable natural resource management and conservation as a result of USG assistance (ROECCR 2.1.1) | 1290 | 40 | 0 | 40 | 220 | FY14 target = 20 people with fisheries livelihoods at each of 2 WASH sites (Sanyang and Tanji) trained in improved fish handling and hygiene. |
| W1a | No of peoples with improved access to sanitation facilities | 0 | 23,175 | 10,058 | 1605 | 23,175 | See LOP footnote above. Old Jeswang, Brufut, Kamalo, Kartong. Sanyang and Tanji still to go in April. |
| W1b | No of people with improved access to water facilities | 0 | 11,663 | 10,058 | 1605 | 11,663 | See LOP footnote above. Old Jeswang, Brufut , Kamalo and Kartong. Target reached in Q2. No additional expected. |
| W2 | Number of persons receiving Participatory Hygiene and Sanitation Transformation (PHAST) Training. | 160 | 80 | 0 | 80 | 240 | FY 14 target = 40 at Sanyang + 40 at Tanji |
| W3 | Number of persons receiving training and outreach messages on hygiene promotion | 0 | 6000 | 3933 | TBD | 6000 | 20 trainers trained in FY13 at each of 4 sites (Brufut, Old Jeshwang, Kartong, Kamalo). These trainers have reached 3933. Last 2 sites (Tanji, Sanyang) will be Q2. Data available in April. |
| W4 | Community water and sanitation committees established and trained with program assistance | 6 | 2 | 0 | 2 | 6 | See LOP footnote above. FY14 = 1 at Sanyang + 1 at Tanji. LOP exceeded due to 2 at Old Jeshwang and 2 at Kartong (separate for oyster and fish sites). |
| 4 | No of institutions with improved capacity to address NR, BD, climate change, water issues as a result of USG assistance (ROECCR 4.1.1) | 17 | 1 | 0 | 0 | 13 | Previous = LACOMS in 7 communities (Gunjur, Brufut, Sanyang, Tanji, Batokunku/Tujereng, Bakau, Banjul), NASCOM, GAMFIDA, NAAFO, TRY, DoFish, NEA, Water Lab, DPWM, TAGFC. FY13 = TARUD, FY 14 target = DOH under GNSSP MOU. DOH is expected in April 2014 plus The Gambia Food Safety and Quality Authority with the signing of the GNSSP MOU. |
| 5 | Number of people receiving USG supported training in natural resources management and/or biodiversity conservation. (F 4.8.1-27) | 1716 | 242 | 38 | 208 | 1958 | = TrainNet. There is duplication of individuals being trained in multiple trainings. |
| 6 | Improvements on governance scorecard | Increasing | na | na | na | increasing | No FY 14 scoring planned as latest was done in late September 2013. |
| No | Indicator | Cumulative Results (as of FY13) | FY14 Target | Q1 | Q2 | LOP Target | Comments |
| 11 | Number of laws, policies, strategies, plans, agreements, or regulations addressing climate change (mitigation or adaptation) and/or biodiversity conservation officially proposed, adopted, or implemented as a result of USG assistance (ROECCR 4.3.1) | 2 | 2 | 1 | 0 | 2 | FY12 = Sole and Oyster Co-Management Plans FY14 = GNSSP MOU + Catfish/gillnet amendment to the Sole Plan. GNSSP MOU signature expected in April |
| CC1 | Number of climate vulnerability assessments conducted as a result of USG assistance | 1 | 0 | 0 | 0 | 1 |  |
| CC2 | Number of stakeholders using climate information in their decision making as a result of USG assistance | 44 | 0 | 0 | 0 | 30 | See LOP comment above |
| CC3 | Number of institutions with improved capacity to address climate change issues as a result of USG assistance | 18 | 0 | 0 | 0 | 8 | See LOP comment above |
| 12 | No. of Hectares in areas of biological significance under improved natural resource management (ROECCR 1.1): • Hectares covered by the fisheries management plan defined as the range of fishing fleets targeting these species • Oyster fishery estuarine and mangrove areas designated and allocated as community managed zones, including no-take areas | Sole = 121,245ha Oyster = Tanbi = 6304ha | 0 0 | 0 0 | 0 0 | FMP Areas: Sole = 12nm seaward = 158,332 ha Community managed oyster zones: TWNP = 6000 ha | See LOP comment above. Hectares maintained. Allahein River estuary co-management planning will still be in process. Catfish amendment to Sole Plan will not add hectares. |
| 17 | No. of HA in areas of biological significance showing improved biophysical conditions as a result of USG assistance. (ROECCR AO1) = Hectares under effective mgt (progress towards BRPs) for sole and oysters |  |  |  |  | No target but tracked | Reference points for sole to be established as part of the management plan. Baseline will be established based on results of preliminary stock assessment Baseline data for oysters collected in year1 PRA |

# Appendix B. USAID ROECCR Results Framework

# Appendix C. Activity Implementation Status

| IR1 Activities | Q1 | Q2 | April |  | Year 5 Quarter 2 Status |
| --- | --- | --- | --- | --- | --- |
| Gazetting of the Sole Co-Management Plan |  |  |  |  | The 2 plans appeared in the Gambia Gazette on December 19, 2013. |
| Complete Seed Grant #2 Capacity Strengthening to NASCOM |  |  |  |  | Planned activities complete. In December a new catfish longline hook study was added to the grant based on stakeholder recommendation for further research. It will be completed in April. |
| - 2nd Annual Co-Management Plan Review Meeting |  |  |  |  | Held in November 2013. |
| - Consult stakeholders on draft Amendment to the Sole Co-Management Plan for Catfish. Possible approval. |  |  |  |  | Done and amendment signed by NASCOM, DoFish and Minister of Fisheries and Water Resources in December 2013. |
| Organize 2nd Annual Bi-lateral Co-Management Meeting (see also IR2) |  |  |  |  | Held in November 2013. |
| Gazetting of the Oyster and Cockle Co-Management Plan |  |  |  |  | The 2 plans appeared in the Gambia Gazette on December 19, 2013. |
| Complete Seed Grant #4 and #5 Capacity Strengthening to TRY |  |  |  |  | Planned activities completed. |
| - 2nd Annual Co-Management Plan Review Meeting |  |  |  |  | Held on January 16, 2014. |
| - Allahein River Estuary bi-lateral co-management process meeting conducted. |  |  |  |  | TRY and DoFish field visit to Southern Senegal communities and meeting held in Kartong, January 9 – 11, 2014. |
| Monthly Water Quality testing continued |  |  |  |  | Completed December 2013. |
| Inter-agency MOU for development of GNSSP – Tanbi developed and signed, including commitments to fund water quality testing by February 2014. |  |  |  |  | Final validation and signature expected in April 2014. |
| Draft GNSSP – Tanbi developed, including training in and preliminary mapping of water quality zones |  |  |  |  | Completed in January 2014. |
| PHAST Training for 2 sites (Sanyang & Tanji) |  |  |  |  | Completed in Q2. |
| Community awareness raising, training and outreach for 2 sites through TOT model (Sanyang & Tanji) |  |  |  |  | Completed in Q2. |
| Management planning final for Kartong, Kamalo |  |  |  |  | Kamalo plan signed in December 2013, Kartong Plan signed in March 2014. |
| Fish Handling and Hygiene Training 2 sites (Sanyang & Tanji) |  |  |  |  | Completed in Q2. |
| Management planning for Sanyang, Tanji |  |  |  |  | To be signed in early April. |
| Environmental Compliance activities at construction sites |  |  |  |  | On-going |
| Site designs for 2 additional sites |  |  |  |  | Completed. |
| Contracting for construction of infrastructure at 2 additional sites |  |  |  |  | Completed. |
| Complete Construction at Kartong, Kamalo |  |  |  |  | Kamalo completed and handed over in December 2013. Kartong completed and handed over in March 2013. |
| Complete Construction at Sanyang, Tanji |  |  |  |  | To be completed in early April. |
| Handover of 4 completed infrastructure |  |  |  |  | Completed December 2013 for 3 sites (Kamalo, Old Jeshwang and Brufut). A total of 5 latrine blocks and 5 water points at 3 sites. Kartong site handed over March 2014 (2 water points 2 latrines). |
| Training in DoFish Supervision and WASH Committee financial management |  |  |  |  | Conducted on January 24, 2014. |
| M&E |  |  |  |  | To be completed in early April, 2014. |
| Handover of last 2 completed infrastructure |  |  |  |  | To be handed over in early April, 2014. |
| IR2 Activities |  |  |  |  | Year 5 Quarter 2 Status |
|  | Q1 | Q2 |  | April |  |
| Assist DoFish Statistics unit to plan for sustainable stock assessment capacity. |  |  |  |  | Completed during Castro visit in November. MOU between NASCOM and DoFish for data collection signed in December 2013. |
| Facilitate Comparative Cost Study draft Cabinet Paper development |  |  |  |  | Will not be achieved. Due to Ousman Drammeh’s passing, this activity did not continue with the momentum it had. |
| Bilateral Co-Management (Gambia/Senegal) 2nd Annual Workshop |  |  |  |  | Held in November 2013. |
| End of Project Stakeholder Review and Closeout Workshop |  |  |  |  | Held on March 27, 2014. |

Note that the Co-Management Plans and most of the other activities described under IR1 also contribute to IRs 2, 3 and 4.  Likewise, some of the activities described under IR2 also contribute to IR1.

Note that many of the activities described under IR1 also contribute to IR2.

The numbers reported for sanitation have been separated from those for water as per USAID standard indicators. The original number of 56,000 was revised downwards to 20,000 in Year 4 due to the larger number of smaller sites selected for the initial round of interventions and the elimination of one of the largest sites, Banjul, due to significant problems with relocation of the landing site as a result of port construction.  In Year 5 it is adjusted to 23,175 based on the data in Annex 4 of the WASH Needs Assessment Validation Workshop Report.  For each of the 6 sites (Brufut, Tanji, Sanyang, Old Jeshwang, Kamalo, and Kartong) the total users plus 25% of the total population as per the 2003 census was used to estimate the number gaining access to the improved facility.

The number for water now that it is separated out is only 11, 663 because at the last 2 WASH sites (Sanyang and Tanji), only sanitation facilities will be added with USG assistance.  Water points already exist.

Scorecard based on governance indicators in UNEP/GPA Ecosystem Based Management Guide

The same individuals may be counted more than once if they received assistance (i.e., training) that improves their economic benefits on multiple occasions in one year or in successive years.

Adjusted up from the 13 reported in the FY12 (Year 3) annual report as NEA, DPWM and Water Lab are in the “previous” group as documented by their repeated participation in various training activities documented in TraiNet.